## SOCO_Modules
PLATO-SOCO Automation Test Cases Development Estimates
S.No | SOCO-Modules | Automation Required(Yes/No)
1 | Daily Accrual | Yes
2 | RFA | Yes
3 | Feed Check | Yes
4 | Fx Rec | Yes
5 | Super Rec | Yes
6 | T0 | Yes
7 | PnL Summary | Yes
8 | Daily Accrual Rates | Yes
9 | RFA Rates | Yes
10 | MTM | Yes
11 | Blotter | Yes
12 | Adjustment | Yes

## Functionality and Scenarios
QA Estimation (Functions and Scenario Coverage) - SOCO
S.No | Functional Description | No.of Test Cases | Complex | Medium | Simple | Comments
1 | Daily Accrual | 1 | 0 | 1 | 0
2 | RFA | 7 | 0 | 1 | 6
3 | Feed Check | 24 | 0 | 24 | 0
4 | Fx Rec | 88 | 72 | 0 | 16
5 | Super Rec | 73 | 11 | 17 | 45
6 | T0 | 15 | 0 | 3 | 12
7 | PnL Summary | 14 | 5 | 9 | 0
8 | Daily Accrual Rates | 31 | 20 | 5 | 6
9 | RFA Rates | 24 | 0 | 3 | 21
10 | MTM | 40 | 7 | 0 | 33
11 | Blotter | 20 | 5 | 4 | 11
12 | Adjustment | 109 | 30 | 19 | 60
Total |  | 446 | 150 | 86 | 210

## Estimated-Effort
QA Estimates_SOCO
Automation Test cases Development - Estimated Effort |  |  |  | Test Case Design - Effort Split up based on Complexity
Complexity | Test Cases | Effort per test case | Effort Reqd (Hours) | Activity | Simple Hrs | Medium Hrs | High Hrs
Simple | 210 | 6 | 1260 | Test Case Analysis | 0.5 | 1 | 1
Medium | 86 | 10 | 860 | Test Data Preparation | 0.5 | 1 | 1
Complex | 150 | 14 | 2100 | Test case/script development | 5 | 8 | 12
|  | Total Effort | 4220 | Total (Hours) | 6 | 10 | 14
Re-use existing TCs |  |  | 422
|  | Total Estimated Effort | 3798
Activities |  | Effort (In Hours)
Estimated Effort required for updation of Object Properties |  | 0
Estimated effort required for project creation in Selenium |  | 4
Buffer Effort |  | 379.8
Total Estimated Effort Required for QA Automation |  | 3798
Overall Estimated Effort for QA automation |  | 4181.8

## Assumption and Dependencies
Note: This sheet is for QA, BA, Dev Team and for PM as well
Assumptions
These estimations are considered to be Final after receiving approval from respective stake holders ,
These estimations are prepared based on the experience and with available existing framework actual test cases development effort
Test(QA) Environment is in Scope for Test case development and execution
SOCO application is in Scope for Test case development and execution
The estimations are prepared assuming that the Environment would be stable during Test case Development in Non-Prod(QA) Environment
It is assumed that user would have access to SOCO application with required access rights
Estimates are subjected to changes if there are any changes to the scope
Estimates are subjected to changes if there are any new requirement added/modified.
100% Front End view of application is considered while developing Test cases
Buffer Effort is considered 10% of estimated Effort
If the validations are include more than 10 steps we have consider it as Complex
If the validations are include between 5-10 steps or old UI to Next Gen UI navigation we have consider it as Medium
If the validations are include below 5 steps we have consider it as Simple
Out Of Scope
No change in the application front end view
Testing in other than I.E and Chrome browsers are out of scope
Validations on Excel sheets are out of scope
Dependencies
QA team need support from Development team during test design if required.

## Scheduled-Resource Load & Effor
Schedule and Effort Summary_SOCO_Selenium Test Case Implementation
Start Date | 2019-06-06
End Date
Phases & Activities | Total Hours | Total Days Per Resource
Updation of Object Properties | 0 | 0
Project creation in Selenium | 4 | 0.5
Buffer Effort | 379.8 | 47.475
QA Automation | 3798 | 474.75
Total Time | 4181.8 | 522.725
Schedule & Resourcing
Phases | Start Date | End Date | Offshore Resource Count | No of Days
Automation Test Script Development | 06-June-19 |  | 2 | 261.3625

## Sheet1 (hidden)
Module | Manual Test cases | Automatable test cases | Test Cases Sheet Considered
Daily Accrual | 4 | 1
RFA | 10 | 7
Feed Check | 24 | 24 | SOCO_Feed_CheckV1.3
Fx Rec | 64 | 88 | SOCO_FX-REC_TestDesignV1.2
Super Rec | 104 | 73 | SOCO_SUPER-REC_TestDesignV1.2
T0 | 60 | 15 | SOCO_T0_TestDesignV1.3
PnL Summary | 79 | 14 | SOCO_SUMMARYPNL_V1.1
Daily Accrual Rates | 47 | 31 | SOCO_Daily_Accrual_Rates_V4.1
RFA Rates | 24 | 24 | SOCO_RFA_RATES_TestDesignV1.0
MTM | 40 | 40 | SOCO_MTMV1.0
Blotter | 68 | 20 | SOCO_BlotterAnalysis_V1.2
Adjustment | 124 | 109
Total |  | 446